## Slide 1: G8T9 Y W L T C
PM Review
Christine | Lifu | Tee Yong | Wang Ting | Yu Liang

## Slide 2: Functionalities

## Slide 3: Do you plan to drop/add any functionalities?
Not dropping any functionalities
Yes, we plan to add functionalities
Starting with recommended ones after completing required functions
Timetable
Search
Consideration for other functions will depend on progress

## Slide 4: Do you plan to use any PHP frameworks?
Didn’t use in Iter 1 & 2
Maybe for additional features in future iterations (need to learn)

## Slide 5: Did you manage to finish +3 functionalities?
Add Bid
Drop Bid
Edit Bid
View Bidding Results
Bootstrap Validation
Token Validation
Start and Clear (Round 1)

## Slide 6: What is the IP address & admin password for your cloud deployment?
Admin password = P@ssw0rd!547
Cloud IP Address = 13.58.117.140/app/login.php

## Slide 7: Schedule

## Slide 8: Project Overall Schedule
Iteration 1 – Login + Bootstrap + Basic UI design
Iteration 2 – Bootstrap Validation, Token Validation, Add Bid, Drop Bid, Edit Bid, Start and Clear Round 1, View Bidding Results, JSON
Iteration 3 – Start and Clear Round 2, Drop Section, Develop additional features + finish UI
Iteration 4 – Fix any bugs, UI, app finalization & deployment
Iteration 5 – Final Presentation

## Slide 9: Project Schedule
Week 5 – Week 6
W5
Week 7 – Week 8
W7
W8
Week 9 – Week 10
W9
W10
Week 11 – Week 13
W11
W12
W13
Iteration 2
(Rounds + user functionalities)
Iteration 3
(Prepare for user testing)
Iteration 4
(Develop additional features)
Iteration 5
(Finishing touch + presentation)
Iteration 1
(Login + Bootstrap)
W6
Completed
Not started
Not started
Not started
LEGEND
PLANNED
ACTUAL
Completed

## Slide 10: Iteration 1 (17/9 – 1/10)
Iteration 1
UI ideation & implementation
Login + database connection
Main page + Logout
Bootstrap & Testing
PLANNED TASKS
SQL + Objects & DAOs
Completed
20/9
21/9
22/9
23/9
24/9
25/9
26/9
27/9
28/9
29/9
30/9
31/9 – 1/10
LEGEND
SCHEDULED
ACTUAL
Completed
Completed
HOLD
Completed
Completed
Completed
HOLD
Completed
Deployment + PM Review
Completed

## Slide 11: Iteration 2 (2/10 – 15/10) (PLANNED)
Iteration 2
Bootstrap
Validation
Add Bid
Edit & Drop Bid
Start & Clear Round
PLANNED TASKS
Token
Validation
2/10 – 3/10
4/10
5/10
6/10
7/10
8/10
9/10
10/10
11/10
12/10
13/10
14/10 – 15/10
LEGEND
PLANNED
ACTUAL
View Bidding Result
JSON
Plan
Deployment & Testing
Plan
Plan
Plan
Plan
Plan
Plan
Plan
Drop Section
Plan

## Slide 12: Iteration 2 (2/10 – 15/10) (ACTUAL)
Iteration 2
Bootstrap
Validation
Add Bid
Edit & Drop Bid
Start & Clear Round
PLANNED TASKS
Token
Validation
2/10 – 3/10
4/10
5/10
6/10
7/10
8/10
9/10
10/10
11/10
12/10
13/10
14/10 - 15/10
LEGEND
PLANNED
ACTUAL
View Bidding Result
Completed
JSON
Completed
Deployment & Testing
Completed
Completed
Completed
Completed
Completed
Completed
Completed

## Slide 13: Iteration 3 (16/10 – 29/10)
Iteration 3
Organizing, tidying up
Drop Section
JSON Test Cases
Start Round 2
PLANNED TASKS
Additional features
16/10
17/10
18/10
19/10
20/10
21/10
22/10
23/10
24/10
25/10
26/10-27/10
28/10 - 29/10
LEGEND
PLANNED
ACTUAL
Testing
Deployment

## Slide 14: Iteration 4 (30/10 – 9/11)
Iteration 4
Organizing, tidying up
Testing
Deployment
Preparation
PLANNED TASKS
Fixing features & UI
30/10
31/10
1/11
2/11
3/11
4/11
5/11
6/11
7/11
8/11
9/11
LEGEND
PLANNED
ACTUAL

## Slide 15: Iteration 5 (9/11 – 19/11)
Iteration 5
Deployment & Submission
Presentation
PLANNED TASKS
Presentation Preparation
10/11
11/11
12/11
13/11
14/11
15/11
16/11
17/11
18/11
19/11
LEGEND
PLANNED
ACTUAL

## Slide 16: What are your milestones?
Milestone 1 – PM Review
Milestone 2 – In-class Demo
Milestone 3 – User Acceptance Test
Milestone 4 – Deployment
Milestone 5 – Final Presentation

## Slide 17: Iteration 1 Critical Path
1
3
1
3
3
3.1.1
0
4
4
5
5
1
3.2.2
1
6
6
6
6
1
3.3.1
0
7
9
7
9
3
3.4.2
0
7
9
10
12
3
3.4.1.2
3
10
10
10
10
1
3.5.1.1
0
13
14
13
14
2
5
0
4
5
4
5
2
3.2.1
0
11
12
11
12
2
3.5.1.2
0
Task ID | Description | Effort
3.1.1 | Create SQL | 3
3.2.1 | Create objects & DAOs | 2
3.2.2 | Set up connection to database | 1
3.3.1 | Create Login | 1
3.4.2 | Create Main page & Logout | 3
3.4.1.2 | Create Login Page UI | 3
3.5.1.1 | Create Bootstrap without validation | 1
3.5.1.2 | Create Bootstrap with validation | 2
5 | Deployment | 2

## Slide 18: Iteration 2 Critical Path (Planned)
1
2
1
2
2
3.1.1
0
3
5
5
7
3
3.6.1
2
5
10
5
10
6
3.3.1
0
11
12
11
12
2
3.3.2
0
6
10
8
12
5
3.6.2
2
13
13
13
13
1
5
0
3
4
3
4
2
3.2.1
0
7
11
8
12
5
3.7.1
1
Task ID | Description | Effort
3.1.1 | Token Authentication | 2
3.2.1 | Bootstrap Validation | 2
3.3.1 | Start and Clear Round | 6
3.3.2 | View Bidding Result | 2
3.5.1. | Drop Section | 1
3.6.1 | Add Bid | 3
3.6.2. , 3.6.3 | Edit and Drop | 5
3.7.1 | JSON | 5
5 | Deployment | 1
11
11
12
12
1
3.5.1
1

## Slide 19: Iteration 2 Critical Path (Actual)
1
2
1
2
2
3.1.1
0
3
6
6
9
4
3.6.1
3
5
11
5
11
6
3.3.1
0
12
12
12
12
2
3.3.2
0
7
9
10
12
3
3.6.2, 3.6.3
3
13
13
13
13
1
5
0
3
4
3
4
2
3.2.1
0
9
12
9
12
4
3.7.1
0
Task ID | Description | Effort
3.1.1 | Token Authentication | 2
3.2.1 | Bootstrap Validation | 2
3.3.1 | Start and Clear Round | 6
3.3.2 | View Bidding Result | 2
3.5.1. | Drop Section | 1
3.6.1 | Add Bid | 4
3.6.2. , 3.6.3 | Edit and Drop | 3
3.7.1 | JSON | 4
5 | Deployment | 1

## Slide 20: How much buffer time do you have?
6 days

## Slide 21: Bug Metrics

## Slide 22
Bug Metrics
(Iter 1)
S/N | Description | Severity | Status
1 | UI - Poor visibility for login page (black text on dark purple BG) | 1 – Low | Resolved
2 | ProcessLogin - Process login failed to redirect to targeted page | 5 – High | Resolved
3 | Bootstrap - Checked wrong columns for pre-requisite.csv | 5 – High | Resolved
4 | Bootstrap – errors output not sorted accordingly to requirements | 1 – Low | Resolved
5 | Login (admin) - No logout button in bootstrap.php after admin login | 5 – High | Resolved
6 | Bootstrap – does not work on AWS | 10 - Critical | Unresolved
Total: 27

## Slide 23
Bug Metrics
(Iter 2)
Total: 87

## Slide 24
Bug Metrics
(Iter 2)
Current: 5

## Slide 25: Roles & Responsibilities

## Slide 26: Iteration 1 – Roles & Responsibilities
Project Manager – Huang Lifu
Coding Team 1 – Yu Liang & Tee Yong
Coding Team 2 – Wang Ting & Christine

## Slide 27: Iteration 2 – Roles & Responsibilities
Project Manager – Wang Ting
Coding Team 1 – Yu Liang & Christine
Coding Team 2 – Li Fu & Tee Yong

## Slide 28: Pair Programming Teams & Rotation Plan

## Slide 29: Pair Programming Teams & Rotation Plan
Iteration | Project Manager | Programming Pairs
1 | Lifu | Yu Liang & Tee Yong Wang Ting & Christine
2 | Wang Ting | Lifu & Tee Yong Yu Liang & Christine
3 | Christine | Yu Liang & Lifu Tee Yong & Wang Ting
4 | Tee Yong | Lifu & Christine Yu Liang & Wang Ting
5 | Yu Liang | N/A

## Slide 30: Thank you!