## Week 5
Person | Question | Week 5: <17/9/2019> to <22/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? |  |  | Going through the project requirements through wiki and learnt about the new requirement changes | Non-Working Day | Non-Working Day | Went through wiki to check for new requirement changes | Non-Working Day
| What will you do today? |  |  | have a group discussion to understand layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | Created sql table using the sql file created done by Lifu and read through the codes uploaded by the team | Non-Working Day
| Do you have any obstacles? |  |  | nil | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Ngo Thanh Van (Christine) | What did you do yesterday? |  |  | I read through the project requirements. | Non-Working Day | Non-Working Day | Met up with Wangting and started coding the UI of the homepage | Non-Working Day
| What will you work on today? |  |  | Discuss the rough page layout and the navigation flow | Non-Working Day | Non-Working Day | Upload the login and its form processing page | Non-Working Day
| Do you have any obstacles? |  |  | Visualising the screens and all the functions | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Tay Yu Liang | What did you do yesterday? |  |  | I read through the newly added project requirements. | Non-Working Day | Non-Working Day | Revising on what was taught last year (eg: php, html) | Non-Working Day
| What will you work on today? |  |  | Group meeting in school from 3.30 to 6.00 to discuss on the page layout and the flow | Non-Working Day | Non-Working Day | Coding of the mainpage, (eg: showing the credit balance, student name, and etc) | Non-Working Day
| Do you have any obstacles? |  |  | I'm a little lost before the meeting but after the meeting, I have a clearer direction. | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Huang Lifu | What did you do yesterday? |  |  | Read through the project requirements, prepare for meeting tomorrow, adjusted our previous schedule accordingly to the new contents and allocated roles | Non-Working Day | Non-Working Day | Revised Data Management materials from last sem, created SQL files for SPM | Non-Working Day
| What will you work on today? |  |  | Set up automatic reminders for daily updates and bug metrics updates, schedule timings for everyone to follow, leran json, github & bootstrap | Non-Working Day | Non-Working Day | Read through teammates' codes, update project schedule file | Non-Working Day
| Do you have any obstacles? |  |  | lack of understanding of json, github, bootstrap | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Toh Wang Ting | What did you do yesterday? |  |  | Going through the project requirements and having a rough idea which tasks to prioritise | Non-Working Day | Non-Working Day | upload the DAOs and classes, meet up with christine for pair programming | Non-Working Day
| What will you work on today? |  |  | have a discussion on the layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | go through and see what other functions are necessary for the DAOs | Non-Working Day
| Do you have any obstacles? |  |  | understanding how the bootstrap, database and json part is linked but i have a clearer understanding of it now after clarifying it with my team member Tee Yong | Non-Working Day | Non-Working Day | NIL | Non-Working Day

## Week 6
Person | Question | Week 6: <23/9/2019> to <29/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Met up with Yu Liang in SMU to do pair programming and completed the display of mainpage and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Non-Working Day | Created and updated test cases in testcase.xlsx | Meet up with Christine to sort the new codes to folders | Non-Working Day
| What will you do today? | Test out the code by everyone and see if there is area of code I do not understand | Non-Working Day | Non-Working Day | Create and update tesetcase.xlsx, account for all possibilities that user could face or try | Meet up with Christine to sort out the new codes to folders | Non-Working Day | Meeting with team, pair programming with Yu Liang for bootstrap with validation
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Pulled the current repo to test run all code files. | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Planned personal milestones and went over project documents | Met up with Yu Liang to do pair programming for UI | Meet up with Tee Yong to sort the new codes to folders | Non-Working Day
| What will you work on today? | brainstorming how to pair the UI design | Non-Working Day | Plan my own milestones to complete the assigned tasks | Meetup with Yu Liang to do pair programming on login UI, consolidated design options that could be applied for our project | Meet up with Tee Yong to sort out the new codes into folders | Non-Working Day | Meeting with team
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Met up with TeeYong to pair programming to complete the main page and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Updated myself on the coding progress of my teammates | Met up with Christine for pair programming for UI | Help to organise the PowerPoint slides | Non-Working Day
| What will you work on today? | look at the codes and analyse what the code is performing. | Non-Working Day | Read through the codes committed by my teammates. | Ideation for UI design options and Pair programming with Christine for UI | Prepare and organize the content for presentation deck for PM review week | Non-Working Day | Meeting with group members + PP for bootstrap (with validation) with Tee Yong
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Reviewed every team members' codes and ensured that everything is done properly. Planned schedule. | Non-Working Day | Conduct group meeting, set new expectations, rules and work methods as previous week was not as effective as expected | Update scheduling, manage pair programming sessions and check through documents | Updated scheduling according to new directions and goals set by team during meeting, updated personal timeline | Pair programming for bootstrap with wangting | Prepare for presentation and meeting delivery
| What will you work on today? | Update schedule, plan meeting content for tomorrow | Non-Working Day | Update scheduling for the team, coordinate pair programming sessions and check through all existing management documents | Continue updating scheduling and coordinate sessions as it took longer than expected | Pair Programming with Wang Ting for Bootstrap | Preparation for tomorrow's meeting and pair programming plans | Edit & finalize PM Review presentation slides
| Do you have any obstacles? | NIL | Non-Working Day | Find tasks time consuming | Not enough understanding on project document, going to re-read it | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | go through and see what other functions are necessary for the DAOs programming | Non-Working Day | Group meeting on schedule, milestones, and progress updates | Compiled minutes and updated my personal schedule accordingly after the changes implemented | Non-Working Day | meet up with Lifu for pair programming on bootstrap | Non-Working Day
| What will you work on today? | check our scheduling | Non-Working Day | commit minutes | Non-Working Day | Pair Programming with Lifu for Bootstrap | Non-Working Day | Meeting with group members, take minutes and note scheduling needs
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL

## Week 7
Person | Question | Week 7: <30/9/2019> to <6/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Meeting with group members . Pair programming for Yu Liang for bootstrap with validation.
| What will you do today? | Meeting with group members to keep everyone on the same page. Check the code to see if there is any errors.
| Do you have any obstacles? | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Meeting with group members. Manual login and json authenticating testing and updating test case file.
| What will you work on today? | Meeting with group members to keep everyone on the same page. Look at UI coding for main page
| Do you have any obstacles? | NIL
Tay Yu Liang | What did you do yesterday? | Meeting with group members . Pair programming for Tee Yong for bootstrap with validation.
| What will you work on today? | Meet up with group members to finalise our slides and keep everyone one the same page.
| Do you have any obstacles? | NIL
Huang Lifu | What did you do yesterday? | Group meeting to address issues with consistency, allocated work and prepared slides for PM review
| What will you work on today? | Group meeting, tidy up iteration 1's work, finish PM review slides and allocate people for testing and deployment
| Do you have any obstacles? | Trouble finding good venues for unplanned meetings & pair programming sessions
Toh Wang Ting | What did you do yesterday? | Meeting with group members. JSON authenticating testing and updating test case file. Committing of minutes.
| What will you work on today? | Meet up with group members to finalise our slides and have everyone on the same page.
| Do you have any obstacles? | NIL