## Week 4 Wed
Person | Question | Week 5: <17/9/2019> to <23/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tee Yong | What did you do yesterday? | Going through the project requirements through wiki and learnt about the new requirement changes
| What will you do today? | have a group discussion to understand layout of website, the flow and functionalities
| Do you have any obstacles? | nil
Ngo Thanh Van (Christine) | What did you do yesterday? | I read through the project requirements.
| What will you work on today? | Discuss the rough page layout and the navigation flow
| Do you have any obstacles? | Visualising the screens and all the functions
Tay Yu Liang | What did you do yesterday? | I read through the newly added project requirements.
| What will you work on today? | Group meeting in school from 3.30 to 6.00 to discuss on the page layout and the flow
| Do you have any obstacles? | I'm a little lost before the meeting but after the meeting, I have a clearer direction.
Huang Lifu | What did you do yesterday? | Read through the project requirements, prepare for meeting tomorrow, adjusted our previous schedule accordingly to the new contents and allocated roles
| What will you work on today? | Prepare database integration and creation of all the necessary documents for the upcoming daily updates and github
| Do you have any obstacles? | lack of understanding of json, github, bootstrap
Toh Wang Ting | What did you do yesterday? | Going through the project requirements and having a rough idea which tasks to prioritise
| What will you work on today? | have a discussion on the layout of website, the flow and functionalities
| Do you have any obstacles? | understanding how the bootstrap, database and json part is linked but i have a clearer understanding of it now after clarifying it with my team member Tee Yong

## Week 4 Thur
Person | Question | Week 5: <17/9/2019> to <23/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tee Yong | What did you do yesterday? | Going through the project requirements through wiki and learnt about the new requirement changes | Non-Working Day
| What will you do today? | have a group discussion to understand layout of website, the flow and functionalities | Non-Working Day
| Do you have any obstacles? | nil | Non-Working Day
Ngo Thanh Van (Christine) | What did you do yesterday? | I read through the project requirements. | Non-Working Day
| What will you work on today? | Discuss the rough page layout and the navigation flow | Non-Working Day
| Do you have any obstacles? | Visualising the screens and all the functions | Non-Working Day
Tay Yu Liang | What did you do yesterday? | I read through the newly added project requirements. | Non-Working Day
| What will you work on today? | Group meeting in school from 3.30 to 6.00 to discuss on the page layout and the flow | Non-Working Day
| Do you have any obstacles? | I'm a little lost before the meeting but after the meeting, I have a clearer direction. | Non-Working Day
Huang Lifu | What did you do yesterday? | Read through the project requirements, prepare for meeting tomorrow, adjusted our previous schedule accordingly to the new contents and allocated roles | Non-Working Day
| What will you work on today? | Set up automatic reminders for daily updates and bug metrics updates, schedule timings for everyone to follow, leran json, github & bootstrap | Non-Working Day
| Do you have any obstacles? | lack of understanding of json, github, bootstrap | Non-Working Day
Toh Wang Ting | What did you do yesterday? | Going through the project requirements and having a rough idea which tasks to prioritise | Non-Working Day
| What will you work on today? | have a discussion on the layout of website, the flow and functionalities | Non-Working Day
| Do you have any obstacles? | understanding how the bootstrap, database and json part is linked but i have a clearer understanding of it now after clarifying it with my team member Tee Yong | Non-Working Day