## Week 5
Person | Question | Week 5: <17/9/2019> to <22/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? |  |  | Going through the project requirements through wiki and learnt about the new requirement changes | Non-Working Day | Non-Working Day | Went through wiki to check for new requirement changes | Non-Working Day
| What will you do today? |  |  | have a group discussion to understand layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | Created sql table using the sql file created done by Lifu and read through the codes uploaded by the team | Non-Working Day
| Do you have any obstacles? |  |  | nil | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Ngo Thanh Van (Christine) | What did you do yesterday? |  |  | I read through the project requirements. | Non-Working Day | Non-Working Day | Met up with Wangting and started coding the UI of the homepage | Non-Working Day
| What will you work on today? |  |  | Discuss the rough page layout and the navigation flow | Non-Working Day | Non-Working Day | Upload the login and its form processing page | Non-Working Day
| Do you have any obstacles? |  |  | Visualising the screens and all the functions | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Tay Yu Liang | What did you do yesterday? |  |  | I read through the newly added project requirements. | Non-Working Day | Non-Working Day | Revising on what was taught last year (eg: php, html) | Non-Working Day
| What will you work on today? |  |  | Group meeting in school from 3.30 to 6.00 to discuss on the page layout and the flow | Non-Working Day | Non-Working Day | Coding of the mainpage, (eg: showing the credit balance, student name, and etc) | Non-Working Day
| Do you have any obstacles? |  |  | I'm a little lost before the meeting but after the meeting, I have a clearer direction. | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Huang Lifu | What did you do yesterday? |  |  | Read through the project requirements, prepare for meeting tomorrow, adjusted our previous schedule accordingly to the new contents and allocated roles | Non-Working Day | Non-Working Day | Revised Data Management materials from last sem, created SQL files for SPM | Non-Working Day
| What will you work on today? |  |  | Set up automatic reminders for daily updates and bug metrics updates, schedule timings for everyone to follow, leran json, github & bootstrap | Non-Working Day | Non-Working Day | Read through teammates' codes, update project schedule file | Non-Working Day
| Do you have any obstacles? |  |  | lack of understanding of json, github, bootstrap | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Toh Wang Ting | What did you do yesterday? |  |  | Going through the project requirements and having a rough idea which tasks to prioritise | Non-Working Day | Non-Working Day | upload the DAOs and classes, meet up with christine for pair programming | Non-Working Day
| What will you work on today? |  |  | have a discussion on the layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | go through and see what other functions are necessary for the DAOs | Non-Working Day
| Do you have any obstacles? |  |  | understanding how the bootstrap, database and json part is linked but i have a clearer understanding of it now after clarifying it with my team member Tee Yong | Non-Working Day | Non-Working Day | NIL | Non-Working Day

## Week 6
Person | Question | Week 6: <23/9/2019> to <29/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Met up with Yu Liang in SMU to do pair programming and completed the display of mainpage and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Non-Working Day | Created and updated test cases in testcase.xlsx | Meet up with Christine to sort the new codes to folders | Non-Working Day
| What will you do today? | Test out the code by everyone and see if there is area of code I do not understand | Non-Working Day | Non-Working Day | Create and update tesetcase.xlsx, account for all possibilities that user could face or try | Meet up with Christine to sort out the new codes to folders | Non-Working Day | Meeting with team, pair programming with Yu Liang for bootstrap with validation
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Pulled the current repo to test run all code files. | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Planned personal milestones and went over project documents | Met up with Yu Liang to do pair programming for UI | Meet up with Tee Yong to sort the new codes to folders | Non-Working Day
| What will you work on today? | brainstorming how to pair the UI design | Non-Working Day | Plan my own milestones to complete the assigned tasks | Meetup with Yu Liang to do pair programming on login UI, consolidated design options that could be applied for our project | Meet up with Tee Yong to sort out the new codes into folders | Non-Working Day | Meeting with team
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Met up with TeeYong to pair programming to complete the main page and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Updated myself on the coding progress of my teammates | Met up with Christine for pair programming for UI | Help to organise the PowerPoint slides | Non-Working Day
| What will you work on today? | look at the codes and analyse what the code is performing. | Non-Working Day | Read through the codes committed by my teammates. | Ideation for UI design options and Pair programming with Christine for UI | Prepare and organize the content for presentation deck for PM review week | Non-Working Day | Meeting with group members + PP for bootstrap (with validation) with Tee Yong
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Reviewed every team members' codes and ensured that everything is done properly. Planned schedule. | Non-Working Day | Conduct group meeting, set new expectations, rules and work methods as previous week was not as effective as expected | Update scheduling, manage pair programming sessions and check through documents | Updated scheduling according to new directions and goals set by team during meeting, updated personal timeline | Pair programming for bootstrap with wangting | Prepare for presentation and meeting delivery
| What will you work on today? | Update schedule, plan meeting content for tomorrow | Non-Working Day | Update scheduling for the team, coordinate pair programming sessions and check through all existing management documents | Continue updating scheduling and coordinate sessions as it took longer than expected | Pair Programming with Wang Ting for Bootstrap | Preparation for tomorrow's meeting and pair programming plans | Edit & finalize PM Review presentation slides
| Do you have any obstacles? | NIL | Non-Working Day | Find tasks time consuming | Not enough understanding on project document, going to re-read it | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | go through and see what other functions are necessary for the DAOs programming | Non-Working Day | Group meeting on schedule, milestones, and progress updates | Compiled minutes and updated my personal schedule accordingly after the changes implemented | Non-Working Day | meet up with Lifu for pair programming on bootstrap | Non-Working Day
| What will you work on today? | check our scheduling | Non-Working Day | commit minutes | Non-Working Day | Pair Programming with Lifu for Bootstrap | Non-Working Day | Meeting with group members, take minutes and note scheduling needs
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL

## Week 7
Person | Question | Week 7: <30/9/2019> to <6/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Meeting with group members . Pair programming for Yu Liang for bootstrap with validation. | Meet up with group members to finalise our slides and fix bugs | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meeting with team to discuss the project in iteration 2 | Pair Programming with lifu to do token verification | Pair Programming with lifu to do bootstrap verification | Meeting with team to update progress, tested bootstrap with Lifu and debugged accordingly
| What will you do today? | Meeting with group members to keep everyone on the same page. Check the code to see if there is any errors. | Meet up for presentation with group members | Meet up with group members to discuss project for iteration 2 | Pair Programming with lifu to do token verification | Pair Programming with lifu to do bootstrap verification | Meet up with team to discuss on progress | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Meeting with group members. Manual login and json authenticating testing and updating test case file. | Meet up with group members to finalise our slides and keep everyone one the same page, pair programming with Yu Liang for the mainpage UI | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meeting with team to discuss the project in iteration 2. Committed the minute of the meeting | Non-Working Day | Pair Programming with Yu Liang to do Add Bid verification | Continue Pair Programming with Yu Liang for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties
| What will you work on today? | Meeting with group members to keep everyone on the same page. Look at UI coding for main page | Meet up with group members to highlight what is happening in iteration 2 and the milestones. | Meet up with group members to discuss project for iteration 2. Committing minutes for meeting. | Non-Working Day | Pair Programming with Yu Liang for Add Bid function | Team meeting to discuss on progression & continue pair programming meet up with Yu Liang to do Add Bid function | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Meeting with group members . Pair programming for Tee Yong for bootstrap with validation. | meet up with group members to finalise our slides and keep everyone one the same page, pair programming with Christine for UI | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Non-Working Day | Pair Programming with Christine for Add Bid function | Continue Pair Programming with Christine for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties
| What will you work on today? | Meet up with group members to finalise our slides and keep everyone one the same page. | Meet up with group members to prepare for things to do in iteration 2 and the milestones. | Meet up with group members to discuss project for iteration 2 | Non-Working Day | Pair Programming with Christine for Add Bid function | Continue Pair Programming with Christine for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Group meeting to address issues with consistency, allocated work and prepared slides for PM review | Finalize PM Review slides with team, deployed app to AWS | Met with teammates before PM review, discussed with the group about the feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Pair Programming with tee yong for token verification | Pair Programming with tee yong to do bootstrap verification | Meeting with team to update progress, tested bootstrap with teeyong and debugged accordingly
| What will you work on today? | Group meeting, tidy up iteration 1's work, finish PM review slides and allocate people for testing and deployment | Prepare for PM Review | Meet up with group members to discuss project for iteration 2 | Pair Programming with Tee Yong to do token verification | Pair Programming with tee yong for bootstrap verification | Team meeting to discuss on progression | Non-Working Day
| Do you have any obstacles? | Trouble finding good venues for unplanned meetings & pair programming sessions | AWS deployment did not go as smoothly as expected, bootstrap not working | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Meeting with group members. JSON authenticating testing and updating test case file. Committing of minutes. | Meeting for PM Review preparation | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Non-Working Day | Looked at the schedule and made some planning | Meeting up with the team to check on everyone's progress and ensure that our schedule is going well
| What will you work on today? | Meet up with group members to finalise our slides and have everyone on the same page. | prepare for iteration 2, short meet up with members to discuss issues to address in tomorrow's meeting | Meet up with group members to discuss project for iteration 2 | Non-Working Day | Look at the schedule and plan accordingly | Have a team meeting to discuss on our progress and update schedule accordingly | Continue updating the schedule
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 8
Person | Question | Week 8: <07/10/2019> to <13/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming for starting & clearing rounds with Lifu | Non-Working Day | Debugging & pair programming for rounds clearing with lifu | Pair programming for clearing rounds with lifu | Pair programming for clearing rounds with lifu
| What will you do today? | Non-Working Day | Pair programming for starting & clearing rounds with Lifu | Non-Working Day | Create test cases for start / clear rounds, continue the development of rounds clearing through pair programming with lifu. | Continue working on rounds clearing with lifu, test teammates' edit & drop bid function and update the documentation accordingly | continue pair programming for clearing round with lifu | pair programming with lifu for view bidding results. Attend team meeting to do final testing & deployment
| Do you have any obstacles? | NIL | Not clear about the requirement on starting & clearing round. Require more understanding | NIL | NIL | error in code causing infinite loop | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming and finished makebid.php + validation with Yu Liang | Look at the requirement of delete and edit bid, draft out the logic | Pair programming with Wangting for JSON authentication. Prepare authentication test cases and testing of Start & Clear Rounds by Lifu and TeeYong. | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Yu Liang. | Fixed bug of missing validations for edit bid with Yu Liang. Tested rounds clearing after they are complete.
| What will you work on today? | Review the codes and prepare for continued pair programming on Add Bids function | Continue to finish the makebid.php + validation | Non-Working Day | Work on JSON with Wang Ting | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Yu Liang. | Fix bug of missing validations for edit bid with Yu Liang. Test rounds clearing after they are complete. | Meeting with team to do final testing & deployment
| Do you have any obstacles? | NIL | Troubleshooting and pair the codes with Yu Liang's | NIL | NIL | Figure out why the e dollar keeps getting updated wrongly | Code conflicts between GET and POST method | NIL
Tay Yu Liang | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming and finished makebid.php + validation with Christine | Look at the requirement of delete and edit bid | Non-Working Day | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Christine | Help to do validation for edit bid with Christine
| What will you work on today? | Non-Working Day | Continue to finish the makebid.php + validation | Look at the requirement of delete and edit bid | Non-Working Day | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Christine | Help to do validation for edit bid with Christine | Meet up with up with the team to do final testing and deployment
| Do you have any obstacles? | NIL | Trying to figure out and troubleshoot why my code doesn’t work | NIL | NIL | Figure out why the e dollar keeps getting updated wrongly | Didn't pull in github for a while which resulted in some clashes between different php files when I'm trying to commit and push codes | NIL
Huang Lifu | What did you do yesterday? | Non-Working Day | Revise & learn relevant php concepts and content to prepare for pair programming today | Pair programming for starting & clearing rounds with Tee Yong | Non-Working Day | Debugging & pair programming for rounds clearing with tee yong | Pair programming for clearing rounds with tee yong | Pair programming for clearing rounds with tee yong
| What will you work on today? | Revise & review php content, prepare for pair programming sessions during the recess week | Pair programming for starting & clearing rounds with tee yong | Non-Working Day | Build test cases for start / clear rounds, debug wherever necessary, continue the development of rounds clearing through pair programming with tee yong, create & update test cases with teammates and schedule debug with tee yong if needed | Continue working on rounds clearing with tee yong, test teammates' edit & drop bid function and update the documentation accordingly | continue pair programming for clearing round with tee yong | pair programming with tee yong for view bidding results & meeting with team to do final testing & deployment
| Do you have any obstacles? | NIL | Hopefully not for the programming of clearing rounds | NIL | having trouble understanding json requirements | Figuring out what causes a code to loop infinitely during the development of rounds clearing | NIL | navigating between all the DAOs to figure out the cause of errors for my code
Toh Wang Ting | What did you do yesterday? | Updated the schedule | Non-Working Day | Preparation of testcases for JSON | Non-Working Day | Pair Programming with Christine for JSON authentication. Prepared the authentication test cases and did testing of Start and Clear Rounds (done by Lifu and Tee Yong) | Pair Programming with Christine on JSON Bootstrap, prepared testcases and did testing, minor adjustment to Bootstrap.php | Scheduling
| What will you work on today? | Non-Working Day | Revise on JSON and prepare some of the testcases | Non-Working Day | Work on JSON with Christine | Pair Programming with Christine today on JSON bootstrap and prepare the test cases. | Scheduling | Pair Programming with Christine on JSON, meeting with the team to do final testing and deployment, prepare for App Demo
| Do you have any obstacles? | NIL | Not really sure how the out testcases syntax for bootstrap should be like | NIL | Finding out the optimal way of doing the testcases for the JSON (it was not as straight forward as I thought) | Scheduling as everyone have commitments so it is hard to fulfil the functions we originally intended / the tasks are taking longer than planned to be completed. | NIL | NIL

## Week 9
Person | Question | Week 9: <14/10/2019> to <20/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Pair programming & debugging with lifu, team meeting to discuss about next iter, final testing & test deployment for iter 2 | resolved bug found in our website while testing. | App Demo in class | Pair programming with Wangting to do bootstrap restructuring. Meeting with team to discuss iteration 3 schedule. | Non-Working Day | Pair programming with Wangting to restructure json with protect | Non-Working Day
| What will you do today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Pair programming with Wangting to restructure JSON with protect | Non-Working Day | Pair programming with Wangting for admin interface display
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Pair programming & debugging with Yu Liang, team meeting to discuss about next iter, final testing & test deployment for iter 2 | further test our app before deployment to ensure that everything is right | App Demo in class | Meeting with team to discuss iteration 3 schedule | Non-Working Day | Tested run the UI for the other existing pages on external software | Pair programming with Yu Liang to update the UI
| What will you work on today? | Further test our app before deployment. Look at the UI for the new pages created | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Look at designing the UI for the other existing pages | Pair programming with Yu Liang to update the UI | Update UI for other existing pages
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Meet up with up with the team to do final testing and deployment | further test our app before deployment to ensure that everything is right | App Demo in class | Meeting with team to discuss iteration 3 schedule. Commit minute for the meeting | Non-Working Day | Non-Working Day | Pair programming with Christine to update the UI
| What will you work on today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Non-Working Day | Pair programming with Christine to update the UI | Pair programming with Lifu for bootstrap display update
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Pair programming & debugging with tee yong, met with team for idea sharing, final testing & test deployment for iter 2 | Debug with teeyong and deploy with PM at night | App Demo in class | Meeting with team to discuss iteration 3 schedule | Non-Working Day | Non-Working Day | Non-Working Day
| What will you work on today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Team meeting to discuss iteration 3 | Non-Working Day | Non-Working Day | Non-Working Day | Pair programming with Yu Liang for bootstrap display update
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Pair Programming with Christine on JSON, Scheduling, Testing and Deployment | Further testing and deployment | App Demo | Pair programming with Teeyong to do bootstrap restructuring. Meeting with team to discuss iteration 3 schedule. | Non-Working Day | Pair programming with Teeyong to restructure json with protect | Non-Working Day
| What will you work on today? | Further testing of our app before deployment | App Demo and Team Meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Pair programming with Teeyong to restructure JSON with protect | Non-Working Day | Pair programming with Teeyong for admin interface display
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 10
Person | Question | Week 10: <21/10/2019> to <27/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Pair programming with Wangting for admin interface display | Non-Working Day | Meet up with the team to discuss on our progress and what we are doing next. Pair programming with Wangting to create JSON Update Bid testcases and resolve bugs | Pair programming with Wangting for modal box (additional feature) | Pair programming with Wangting on Drop Student Section + testcases for JSON | Work on Modal box CSS | Pair programming with Wangting on JSON bid status
| What will you do today? | Non-Working Day | Meet with team to update on our progress and discuss on what to do next. Pair programming with Wangting to work on JSON update bid testcase | Pair programming with Wangting on modal box (additional feature) | Pair programming with Wangting in Drop Section + test cases for JSON | Work on Modal box CSS | Pair programming with Wang Ting on JSON bid status | Pair programming with Wangting on enhancing edit function for round 2, modal box and view timetable and team meeting afterwards
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Start on coding UI for other existing pages | Pair programming with Yu Liang to update the UI for editBid.php | Meet up with the team to discuss on our progress and what we are doing next. Pair programming with Yu Liang to update bug metrics, testcases, resolve bugs from Add Bid, and update UI | Update UI with Yu Liang | Non-Working Day | Graph the critical path and look at tidying up the schedule | Update the schedule, fix low severity bug and update bug metrics with Yu Liang, update UI for deletebid
| What will you work on today? | Refine and push the codes for UI updates | Meet up with the team to discuss on our progress and what we are doing next. | Look at refining the UI for the pages | Non-Working Day | Update UI for existing pages. Tidy up the schedule | Update the schedule | Meeting with team to finalise the preparation for app deployment
| Do you have any obstacles? | New codes committed amidst the progress of pairing the UI to the back-end, causing conflicts | NIL | New codes committed amidst the progress of pairing the UI to the back-end, some old UI deleted, causing conflicts | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Pair programming with Lifu for bootstrap display update | Pair programming with Lifu for round 2 user features (view min bid, view course details). Pair programming with Christine to update the UI of editBid.php | Meet up with the team to discuss on our progress and what we are doing next. Pair programming with Christine to update bug metrics, testcases, resolve bugs from Add Bid, and update UI | Pair programming with Lifu for Rounds clearing and commit minutes of the meeting | Pair programming with Lifu for search function and finalise rounds clearing | Pair programming with Lifu for search function and rounds clearing, update bug metrics | Pair programming with Lifu to update clearing logic for JSON start stop
| What will you work on today? | Pair programming with Lifu for Round 2 user features (view module details, view biddable modules, shortcut buttons,...) | Meet up with the team to discuss on our progress and what we are doing next. | Pair programming with Lifu for rounds clearing and commit minutes for meeting | Pair programming with Lifu for search function and finalise rounds clearing | Pair programming with Lifu for rounds clearing | Pair programming with Lifu for JSON start stop and to update clearing logic | Pair programming with Lifu for additional features and UI and team meeting afterwards
| Do you have any obstacles? | NIL | Figuring out how to code the search functionality | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Pair programming with Yu Liang for bootstrap display update | Pair programming with Lifu for round 2 user features (view min bid, view course details) | Meet up with the team to discuss on our progress and what we are doing next. | Pair programming with Yu Liang for Rounds clearing | Pair programming with Yu Liang for search function and finalise rounds clearing | Pair programming with Yu Liang for search function and rounds clearing, update bug metrics | Pair programming with Yu Liang to update clearing logic for JSON start stop
| What will you work on today? | Pair programming with Yu Liang for Round 2 user features (view module details, view biddable modules, shortcut buttons,...) | Meet up with the team to discuss on our progress and what we are doing next. | Pair programming with Yu Liang for rounds clearing | Pair programming with Yu Liang for search function and finalise rounds clearing | Pair programming with Yu Liang for rounds clearing | Pair programming with Yu Liang for JSON start stop and to update clearing logic | Pair programming with Yu Liang for additional features and UI and team meeting afterwards
| Do you have any obstacles? | NIL | Figuring out how to code the search functionality | NIL | NIL | NIL | NIL | Early phase of learning and trying javascript & CSS
Toh Wang Ting | What did you do yesterday? | Pair programming with Teeyong for admin interface display | Non-Working Day | Meet up with the team to discuss on our progress and what we are doing next. Pair programming with Teeyong to create JSON Update Bid testcases and resolve bugs | Pair programming with Teeyong for modal box (additional feature) | Pair programming with Teeyong on Drop Student Section + testcases for JSON | Work on Modal box CSS | Pair programming with Teeyong on JSON bid status
| What will you work on today? | Non-Working Day | Meet up with the team to discuss on our progress and what we are doing next. Work on JSON testcases with Teeyong. | Pair programming with Teeyong on modal box (additional feature) | Pair programming with Teeyong for Drop Section and create JSON test cases | Work on Modal box CSS | Pair programming with Tee Yong on JSON bid status | Pair programming with Tee Yong on enhancing edit function for round 2, modal box and view timetable and team meeting afterwards
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 11
Person | Question | Week 11: <28/10/2019> to <03/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Pair programming with Wangting on enhancing edit function for round 2 and view timetable and team meeting afterwards | Pair programming with Wangting for JSON test cases & modal box. Prepare for final deployment | UAT Testing | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Not a working day | Not a working day
| What will you do today? | Pair programming with Wangting for JSON test cases & modal box. Prepare for final deployment | Pair programming with Lifu to debug + update json test cases, final deployment | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Not a working day | Not a working day | Pair Programming with Lifu to develop JSON test cases
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Meeting with team to finalise the preparation for app deployment. Update the schedule. | Update UI for user pages. Prepare for final deployment | UAT Testing | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Pair programming with Wangting to update UI for user page | Not a working day
| What will you work on today? | Update UI for user pages. Prepare for final deployment | Pair programming with Wang Ting for debugging and tidying up, Final deployment & UAT | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Pair programming with Wangting to update UI for user page | Not a working day | Pair Programming with Wang Ting to update UI for admin page
| Do you have any obstacles? | Restructuring the schedule correctly | NIL | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Pair programming with Lifu for additional features (view completed course) and UI and team meeting afterwards | Pair programming with Lifu for admin UI and perform manual testing. Prepare for final deployment | UAT Testing | PP with lifu for debug some issues found in UAT and discuss on iteration 4 with the team | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pair programming with Lifu for admin UI and perform manual testing. Prepare for final deployment | Pair programming with Lifu for admin page UI and final deployment | PP with lifu for debug some issues found in UAT and discuss on iteration 4 with the team | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Pair programming with Yu Liang for additional features (view completed course) and UI and team meeting afterwards | Pair programming with Yu Liang for admin UI and perform manual testing. Prepare for final deployment | UAT Testing | Meeting with team to discuss iteration 4 and pair programming with Yu Liang in the evening to debug some issues found in UAT | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pair programming with Yu Liang for admin UI and perform manual testing. Prepare for final deployment | Pair programming with Yu Liang for admin page UI and with Tee Yong for JSON checking, then deployment | Meeting with team to discuss iteration 4 and pair programming with Yu Liang in the evening to debug some issues found in UAT | Upload meeting minutes | Not a working day | Not a working day | Pair Programming with Tee Yong to develop JSON test cases
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Pair programming with Teeyong on enhancing edit function for round 2 and view timetable and team meeting afterwards | Pair programming with Teeyong for Modal box & JSON test cases. Prepare for final deployment | UAT Testing | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Pair programming with Christine to update UI for user page | Not a working day
| What will you work on today? | Pair programming with Teeyong for Modal box & JSON test cases. Prepare for final deployment | Pair programming with Christine for debugging and tidying up, update BM and testcases. Final deployment & UAT | Meeting with team to discuss iteration 4 and look at bugs found during UAT | Not a working day | Pair programming with Christine to update UI for user page | Not a working day | Pair Programming with Christine to update UI for admin page
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 12
Person | Question | Week 12: <04/11/2019> to <10/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Pair Programming with Lifu to develop JSON test cases | Not a working day | Not a working day | Pair Programming with Wang Ting for JSON debugging | Not a working day | Not a working day | Not a working day
| What will you do today? | Not a working day | Not a working day | Pair Programming with Wang Ting for JSON debugging | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Update UI for admin page with Wangting (partially completed) | Pair Programming with Wang Ting to update Student main page(incomplete) | Pair Programming with Wang Ting to update Student main page | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pair Programming with Wangting to update UI for user page | Pair Programming with Wang Ting to update Student main page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Not a working day | Not a working day | Pair Programming with Lifu for debugging | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Pair Programming with Lifu for debugging | Not a working day | Not a working day | Pair programming debugging with Lifu and update JSON test cases | Not a working day | Pair programming with Lifu for debugging
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Pair Programming with Tee Yong to develop JSON test cases | Not a working day | Pair Programming with Yu Liang for debugging | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Pair Programming with Yu Liang for debugging | Not a working day | Not a working day | Pair programming debugging with Yu Liang and update JSON test cases | Not a working day | Pair programming with Yu Liang for debugging
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Update UI for admin page with Christine (partially completed) | Pair Programming with Christine to update Student main page(incomplete) | Pair Programming with Christine to update Student main page | Pair Programming with Tee Yong for JSON debugging | Not a working day | Not a working day | Not a working day
| What will you work on today? | Pair Programming with Christine to update UI for user page | Pair Programming with Christine to update Student main page | Pair Programming with Tee Yong for JSON debugging | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 13
Person | Question | Week 12: <11/11/2019> to <17/11/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Not a working day
| What will you do today? | Pair programming with Yu Liang for debugging
| Do you have any obstacles? | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Not a working day
| What will you work on today? | Not a working day
| Do you have any obstacles? | NIL
Tay Yu Liang | What did you do yesterday? | Pair programming with Lifu for debugging
| What will you work on today? | Pair programming with Tee Yong for debugging
| Do you have any obstacles? | NIL
Huang Lifu | What did you do yesterday? | Pair programming with Yu Liang for debugging
| What will you work on today? | Not a working day
| Do you have any obstacles? | NIL
Toh Wang Ting | What did you do yesterday? | Not a working day
| What will you work on today? | Not a working day
| Do you have any obstacles? | NIL