## Week 5
Person | Question | Week 5: <17/9/2019> to <22/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? |  |  | Going through the project requirements through wiki and learnt about the new requirement changes | Non-Working Day | Non-Working Day | Went through wiki to check for new requirement changes | Non-Working Day
| What will you do today? |  |  | have a group discussion to understand layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | Created sql table using the sql file created done by Lifu and read through the codes uploaded by the team | Non-Working Day
| Do you have any obstacles? |  |  | nil | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Ngo Thanh Van (Christine) | What did you do yesterday? |  |  | I read through the project requirements. | Non-Working Day | Non-Working Day | Met up with Wangting and started coding the UI of the homepage | Non-Working Day
| What will you work on today? |  |  | Discuss the rough page layout and the navigation flow | Non-Working Day | Non-Working Day | Upload the login and its form processing page | Non-Working Day
| Do you have any obstacles? |  |  | Visualising the screens and all the functions | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Tay Yu Liang | What did you do yesterday? |  |  | I read through the newly added project requirements. | Non-Working Day | Non-Working Day | Revising on what was taught last year (eg: php, html) | Non-Working Day
| What will you work on today? |  |  | Group meeting in school from 3.30 to 6.00 to discuss on the page layout and the flow | Non-Working Day | Non-Working Day | Coding of the mainpage, (eg: showing the credit balance, student name, and etc) | Non-Working Day
| Do you have any obstacles? |  |  | I'm a little lost before the meeting but after the meeting, I have a clearer direction. | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Huang Lifu | What did you do yesterday? |  |  | Read through the project requirements, prepare for meeting tomorrow, adjusted our previous schedule accordingly to the new contents and allocated roles | Non-Working Day | Non-Working Day | Revised Data Management materials from last sem, created SQL files for SPM | Non-Working Day
| What will you work on today? |  |  | Set up automatic reminders for daily updates and bug metrics updates, schedule timings for everyone to follow, leran json, github & bootstrap | Non-Working Day | Non-Working Day | Read through teammates' codes, update project schedule file | Non-Working Day
| Do you have any obstacles? |  |  | lack of understanding of json, github, bootstrap | Non-Working Day | Non-Working Day | NIL | Non-Working Day
Toh Wang Ting | What did you do yesterday? |  |  | Going through the project requirements and having a rough idea which tasks to prioritise | Non-Working Day | Non-Working Day | upload the DAOs and classes, meet up with christine for pair programming | Non-Working Day
| What will you work on today? |  |  | have a discussion on the layout of website, the flow and functionalities | Non-Working Day | Non-Working Day | go through and see what other functions are necessary for the DAOs | Non-Working Day
| Do you have any obstacles? |  |  | understanding how the bootstrap, database and json part is linked but i have a clearer understanding of it now after clarifying it with my team member Tee Yong | Non-Working Day | Non-Working Day | NIL | Non-Working Day

## Week 6
Person | Question | Week 6: <23/9/2019> to <29/9/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Met up with Yu Liang in SMU to do pair programming and completed the display of mainpage and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Non-Working Day | Created and updated test cases in testcase.xlsx | Meet up with Christine to sort the new codes to folders | Non-Working Day
| What will you do today? | Test out the code by everyone and see if there is area of code I do not understand | Non-Working Day | Non-Working Day | Create and update tesetcase.xlsx, account for all possibilities that user could face or try | Meet up with Christine to sort out the new codes to folders | Non-Working Day | Meeting with team, pair programming with Yu Liang for bootstrap with validation
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Pulled the current repo to test run all code files. | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Planned personal milestones and went over project documents | Met up with Yu Liang to do pair programming for UI | Meet up with Tee Yong to sort the new codes to folders | Non-Working Day
| What will you work on today? | brainstorming how to pair the UI design | Non-Working Day | Plan my own milestones to complete the assigned tasks | Meetup with Yu Liang to do pair programming on login UI, consolidated design options that could be applied for our project | Meet up with Tee Yong to sort out the new codes into folders | Non-Working Day | Meeting with team
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Met up with TeeYong to pair programming to complete the main page and bidded module of the user | Non-Working Day | Group meeting on schedule, milestones, and progress updates. | Updated myself on the coding progress of my teammates | Met up with Christine for pair programming for UI | Help to organise the PowerPoint slides | Non-Working Day
| What will you work on today? | look at the codes and analyse what the code is performing. | Non-Working Day | Read through the codes committed by my teammates. | Ideation for UI design options and Pair programming with Christine for UI | Prepare and organize the content for presentation deck for PM review week | Non-Working Day | Meeting with group members + PP for bootstrap (with validation) with Tee Yong
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Reviewed every team members' codes and ensured that everything is done properly. Planned schedule. | Non-Working Day | Conduct group meeting, set new expectations, rules and work methods as previous week was not as effective as expected | Update scheduling, manage pair programming sessions and check through documents | Updated scheduling according to new directions and goals set by team during meeting, updated personal timeline | Pair programming for bootstrap with wangting | Prepare for presentation and meeting delivery
| What will you work on today? | Update schedule, plan meeting content for tomorrow | Non-Working Day | Update scheduling for the team, coordinate pair programming sessions and check through all existing management documents | Continue updating scheduling and coordinate sessions as it took longer than expected | Pair Programming with Wang Ting for Bootstrap | Preparation for tomorrow's meeting and pair programming plans | Edit & finalize PM Review presentation slides
| Do you have any obstacles? | NIL | Non-Working Day | Find tasks time consuming | Not enough understanding on project document, going to re-read it | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | go through and see what other functions are necessary for the DAOs programming | Non-Working Day | Group meeting on schedule, milestones, and progress updates | Compiled minutes and updated my personal schedule accordingly after the changes implemented | Non-Working Day | meet up with Lifu for pair programming on bootstrap | Non-Working Day
| What will you work on today? | check our scheduling | Non-Working Day | commit minutes | Non-Working Day | Pair Programming with Lifu for Bootstrap | Non-Working Day | Meeting with group members, take minutes and note scheduling needs
| Do you have any obstacles? | NIL | Non-Working Day | NIL | NIL | NIL | NIL | NIL

## Week 7
Person | Question | Week 7: <30/9/2019> to <6/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Meeting with group members . Pair programming for Yu Liang for bootstrap with validation. | Meet up with group members to finalise our slides and fix bugs | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meeting with team to discuss the project in iteration 2 | Pair Programming with lifu to do token verification | Pair Programming with lifu to do bootstrap verification | Meeting with team to update progress, tested bootstrap with Lifu and debugged accordingly
| What will you do today? | Meeting with group members to keep everyone on the same page. Check the code to see if there is any errors. | Meet up for presentation with group members | Meet up with group members to discuss project for iteration 2 | Pair Programming with lifu to do token verification | Pair Programming with lifu to do bootstrap verification | Meet up with team to discuss on progress | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Meeting with group members. Manual login and json authenticating testing and updating test case file. | Meet up with group members to finalise our slides and keep everyone one the same page, pair programming with Yu Liang for the mainpage UI | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meeting with team to discuss the project in iteration 2. Committed the minute of the meeting | Non-Working Day | Pair Programming with Yu Liang to do Add Bid verification | Continue Pair Programming with Yu Liang for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties
| What will you work on today? | Meeting with group members to keep everyone on the same page. Look at UI coding for main page | Meet up with group members to highlight what is happening in iteration 2 and the milestones. | Meet up with group members to discuss project for iteration 2. Committing minutes for meeting. | Non-Working Day | Pair Programming with Yu Liang for Add Bid function | Team meeting to discuss on progression & continue pair programming meet up with Yu Liang to do Add Bid function | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Meeting with group members . Pair programming for Tee Yong for bootstrap with validation. | meet up with group members to finalise our slides and keep everyone one the same page, pair programming with Christine for UI | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Non-Working Day | Pair Programming with Christine for Add Bid function | Continue Pair Programming with Christine for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties
| What will you work on today? | Meet up with group members to finalise our slides and keep everyone one the same page. | Meet up with group members to prepare for things to do in iteration 2 and the milestones. | Meet up with group members to discuss project for iteration 2 | Non-Working Day | Pair Programming with Christine for Add Bid function | Continue Pair Programming with Christine for Add Bid function & Meeting up with the team to update on our progress and discuss if we faced and difficulties | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Group meeting to address issues with consistency, allocated work and prepared slides for PM review | Finalize PM Review slides with team, deployed app to AWS | Met with teammates before PM review, discussed with the group about the feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Pair Programming with tee yong for token verification | Pair Programming with tee yong to do bootstrap verification | Meeting with team to update progress, tested bootstrap with teeyong and debugged accordingly
| What will you work on today? | Group meeting, tidy up iteration 1's work, finish PM review slides and allocate people for testing and deployment | Prepare for PM Review | Meet up with group members to discuss project for iteration 2 | Pair Programming with Tee Yong to do token verification | Pair Programming with tee yong for bootstrap verification | Team meeting to discuss on progression | Non-Working Day
| Do you have any obstacles? | Trouble finding good venues for unplanned meetings & pair programming sessions | AWS deployment did not go as smoothly as expected, bootstrap not working | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Meeting with group members. JSON authenticating testing and updating test case file. Committing of minutes. | Meeting for PM Review preparation | Meet up with group members to finalise our slides and keep everyone on the same page, discussed with the group about feedback from PM review | Meet up with the team to discuss the project requirements in Interation 2. | Non-Working Day | Looked at the schedule and made some planning | Meeting up with the team to check on everyone's progress and ensure that our schedule is going well
| What will you work on today? | Meet up with group members to finalise our slides and have everyone on the same page. | prepare for iteration 2, short meet up with members to discuss issues to address in tomorrow's meeting | Meet up with group members to discuss project for iteration 2 | Non-Working Day | Look at the schedule and plan accordingly | Have a team meeting to discuss on our progress and update schedule accordingly | Continue updating the schedule
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 8
Person | Question | Week 8: <07/10/2019> to <13/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming for starting & clearing rounds with Lifu | Non-Working Day | Debugging & pair programming for rounds clearing with lifu | Pair programming for clearing rounds with lifu | Pair programming for clearing rounds with lifu
| What will you do today? | Non-Working Day | Pair programming for starting & clearing rounds with Lifu | Non-Working Day | Create test cases for start / clear rounds, continue the development of rounds clearing through pair programming with lifu. | Continue working on rounds clearing with lifu, test teammates' edit & drop bid function and update the documentation accordingly | continue pair programming for clearing round with lifu | pair programming with lifu for view bidding results. Attend team meeting to do final testing & deployment
| Do you have any obstacles? | NIL | Not clear about the requirement on starting & clearing round. Require more understanding | NIL | NIL | error in code causing infinite loop | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming and finished makebid.php + validation with Yu Liang | Look at the requirement of delete and edit bid, draft out the logic | Pair programming with Wangting for JSON authentication. Prepare authentication test cases and testing of Start & Clear Rounds by Lifu and TeeYong. | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Yu Liang. | Fixed bug of missing validations for edit bid with Yu Liang. Tested rounds clearing after they are complete.
| What will you work on today? | Review the codes and prepare for continued pair programming on Add Bids function | Continue to finish the makebid.php + validation | Non-Working Day | Work on JSON with Wang Ting | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Yu Liang. | Fix bug of missing validations for edit bid with Yu Liang. Test rounds clearing after they are complete. | Meeting with team to do final testing & deployment
| Do you have any obstacles? | NIL | Troubleshooting and pair the codes with Yu Liang's | NIL | NIL | Figure out why the e dollar keeps getting updated wrongly | Code conflicts between GET and POST method | NIL
Tay Yu Liang | What did you do yesterday? | Non-Working Day | Non-Working Day | Pair programming and finished makebid.php + validation with Christine | Look at the requirement of delete and edit bid | Non-Working Day | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Christine | Help to do validation for edit bid with Christine
| What will you work on today? | Non-Working Day | Continue to finish the makebid.php + validation | Look at the requirement of delete and edit bid | Non-Working Day | Continue pair programming and prepare test cases for bootstrap. Push edit & drop bid functions with Christine | Help to do validation for edit bid with Christine | Meet up with up with the team to do final testing and deployment
| Do you have any obstacles? | NIL | Trying to figure out and troubleshoot why my code doesn’t work | NIL | NIL | Figure out why the e dollar keeps getting updated wrongly | Didn't pull in github for a while which resulted in some clashes between different php files when I'm trying to commit and push codes | NIL
Huang Lifu | What did you do yesterday? | Non-Working Day | Revise & learn relevant php concepts and content to prepare for pair programming today | Pair programming for starting & clearing rounds with Tee Yong | Non-Working Day | Debugging & pair programming for rounds clearing with tee yong | Pair programming for clearing rounds with tee yong | Pair programming for clearing rounds with tee yong
| What will you work on today? | Revise & review php content, prepare for pair programming sessions during the recess week | Pair programming for starting & clearing rounds with tee yong | Non-Working Day | Build test cases for start / clear rounds, debug wherever necessary, continue the development of rounds clearing through pair programming with tee yong, create & update test cases with teammates and schedule debug with tee yong if needed | Continue working on rounds clearing with tee yong, test teammates' edit & drop bid function and update the documentation accordingly | continue pair programming for clearing round with tee yong | pair programming with tee yong for view bidding results & meeting with team to do final testing & deployment
| Do you have any obstacles? | NIL | Hopefully not for the programming of clearing rounds | NIL | having trouble understanding json requirements | Figuring out what causes a code to loop infinitely during the development of rounds clearing | NIL | navigating between all the DAOs to figure out the cause of errors for my code
Toh Wang Ting | What did you do yesterday? | Updated the schedule | Non-Working Day | Preparation of testcases for JSON | Non-Working Day | Pair Programming with Christine for JSON authentication. Prepared the authentication test cases and did testing of Start and Clear Rounds (done by Lifu and Tee Yong) | Pair Programming with Christine on JSON Bootstrap, prepared testcases and did testing, minor adjustment to Bootstrap.php | Scheduling
| What will you work on today? | Non-Working Day | Revise on JSON and prepare some of the testcases | Non-Working Day | Work on JSON with Christine | Pair Programming with Christine today on JSON bootstrap and prepare the test cases. | Scheduling | Pair Programming with Christine on JSON, meeting with the team to do final testing and deployment, prepare for App Demo
| Do you have any obstacles? | NIL | Not really sure how the out testcases syntax for bootstrap should be like | NIL | Finding out the optimal way of doing the testcases for the JSON (it was not as straight forward as I thought) | Scheduling as everyone have commitments so it is hard to fulfil the functions we originally intended / the tasks are taking longer than planned to be completed. | NIL | NIL

## Week 9
Person | Question | Week 9: <14/10/2019> to <20/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday? | Pair programming & debugging with lifu, team meeting to discuss about next iter, final testing & test deployment for iter 2 | resolved bug found in our website while testing. | App Demo in class | Pair programming with Wangting to do bootstrap restructuring. Meeting with team to discuss iteration 3 schedule. | Non-Working Day
| What will you do today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Pair programming with Wangting to restructure JSON with protect
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Ngo Thanh Van (Christine) | What did you do yesterday? | Pair programming & debugging with Yu Liang, team meeting to discuss about next iter, final testing & test deployment for iter 2 | further test our app before deployment to ensure that everything is right | App Demo in class | Meeting with team to discuss iteration 3 schedule | Non-Working Day
| What will you work on today? | Further test our app before deployment. Look at the UI for the new pages created | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Look at designing the UI for the other existing pages
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Tay Yu Liang | What did you do yesterday? | Meet up with up with the team to do final testing and deployment | further test our app before deployment to ensure that everything is right | App Demo in class | Meeting with team to discuss iteration 3 schedule. Commit minute for the meeting | Non-Working Day
| What will you work on today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Huang Lifu | What did you do yesterday? | Pair programming & debugging with tee yong, met with team for idea sharing, final testing & test deployment for iter 2 | Debug with teeyong and deploy with PM at night | App Demo in class | Meeting with team to discuss iteration 3 schedule | Non-Working Day
| What will you work on today? | further test our app before deployment to ensure that everything is right | App Demo and team meeting | Team meeting to discuss iteration 3 | Non-Working Day | Non-Working Day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL
Toh Wang Ting | What did you do yesterday? | Pair Programming with Christine on JSON, Scheduling, Testing and Deployment | Further testing and deployment | App Demo | Pair programming with Teeyong to do bootstrap restructuring. Meeting with team to discuss iteration 3 schedule. | Non-Working Day
| What will you work on today? | Further testing of our app before deployment | App Demo and Team Meeting | Meet with the team and discuss on iter 3 and task allocation | Non-Working Day | Pair programming with Teeyong to restructure JSON with protect
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL

## Week 10
Person | Question | Week 10: <21/10/2019> to <27/10/2019>
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Neo Tee Yong | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Ngo Thanh Van (Christine) | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Tay Yu Liang | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Huang Lifu | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Toh Wang Ting | What did you do yesterday?
What will you work on today?
Do you have any obstacles?