## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | UI | Visibility is poor for login page (black text on dark purple background) | Resolved | 2019-09-27 | 2019-09-30 | C & WT
2 | 1 | ProcessLogin | Failed to redirect to the targeted page | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
3 | 1 | Bootstrap | Checked the wrong columns for pre-requisite.csv | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
4 | 1 | Bootstrap | Bootstrap errors output not sorted accordingly to the JSON requirements | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
5 | 1 | Login (admin) | No logout button in bootstrap.php that admin is directed to | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
6 | 1 | Bootstrap | Bootstrap does not work on AWS after deployment | Resolved | 31/09/2019 | 2019-10-12 | By IS212 team
7 | 2 | Bootstrap Validation | Bootstrap proceeds to check file-specific validations after detecting a blank field | Resolved | 2019-10-05 | 2019-10-05 | TY & LF
8 | 2 | Bootstrap Validation | Bootstrap does not check for exam start & end time properly | Resolved | 2019-10-05 | 2019-10-05 | TY & LF
9 | 2 | Rounds Clearing | Clicking on "Start Round" in Round 1 does not direct the admin to bootstrap | Resolved | 2019-10-10 | 2019-10-10 | TY & LF
10 | 2 | Rounds Clearing | Clicking on "Import" at bootstrap without uploading bootstrap file starts the round | Resolved | 2019-10-10 | 2019-10-18 | Remark: Is not a bug
11 | 2 | Edit Bid | Missing token authentication, fails to proceed, redirected to login | Resolved | 2019-10-10 | 2019-10-11 | C & YL
12 | 2 | Bid | Total bidded amount calculation works incorrectly, resulting in wrong E-dollar amount in database | Resolved | 2019-10-11 | 2019-10-12 | C & YL
13 | 2 | JSON Bootstrap | Failed to check for special condition in bootstrap | Resolved | 2019-10-11 | 2019-10-11 | WT & C
14 | 2 | Edit Bid | Missing some necessary validations | Resolved | 2019-10-11 | 2019-10-12 | C & YL
15 | 2 | Rounds Clearing | Rounds display "Successful / Unsuccessful" instead of "Success / Fail" | Resolved | 2019-10-11 | 2019-10-12 | TY & LF
16 | 2 | Rounds Clearing | Bid results only display for admin after clicking "clear round", refreshing the page will remove the bid results | Resolved | 2019-10-12 | 2019-10-13 | TY & LF
17 | 2 | Rounds Clearing | A bid that should be successful went through as unsuccessful | Resolved | 2019-10-12 | 2019-10-13 | TY & LF
18 | 2 | Rounds Clearing | Admin main page does not display "round is currently ongoing / inactive" after round 2 starts | Resolved | 2019-10-13 | 2019-10-13 | TY & LF
19 | 2 | Edit Bid | Bid can still be dropped after round closes, user will get back double the credits if bid failed, and will get back the credits if bid succeeded | Resolved | 2019-10-13 | 2019-10-13 | C & YL
20 | 2 | Edit Bid | If a user types in valid course code, section, amount but it does not exist in "bidded", the user will be bounced back to the main page (nothing changes) | Resolved | 2019-10-13 | 2019-10-13 | C & YL
21 | 2 | AWS Deployment - section dump JSON | Section Dump does not work on AWS | Resolved | 2019-10-13 | 2019-10-13 | TY & LF
22 | 2 | AWS Deployment - JSON checker | Test Case 115-bootstrap.txt does not work on AWS | Resolved | 2019-10-13 | 2019-10-14 | TY & LF
23 | 2 | Add Bid | Bid is created as object in one function but as list in another, causing some functions to not work | Resolved | 2019-10-13 | 2019-10-14 | TY & LF
24 | 3 | JSON | Section Dump, Bid Dump, delete Bid, Drop Section, Update Bid Files need to be upper case. | Resolved | 2019-10-22 | 2019-11-22 | TY & WT
25 | 3 | Edit Bid | Edit bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | Resolved | 2019-10-22 | 2019-10-22 | C & YL
26 | 3 | Add Bid | Add bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | Resolved | 2019-10-22 | 2019-10-22 | C & YL
27 | 3 | Add Bid | Round 2 for Add bid, System did not validate if the user did enter amount higher than the Minimum Bid Required | Resolved | 2019-10-22 | 2019-10-22 | C & YL
27 | 3 | View Bidding Results | Min Bid Required reflects "14" although the user bidded for 12 and succeeded | Resolved | 2019-10-23 | 2019-10-24 | TY & WT
27 | 3 | Rounds Clearing | Ben's bid is stored as "Success" although it is lower than the minimum amount | Resolved | 2019-10-23 | 2019-10-25 | LF & YL
27 | 3 | Add Bid | Error displayed when trying to add a bid | Resolved | 2019-10-25 | 2019-10-25 | LF & YL
27 | 3 | Round 2 | Bid Result displays "Pending" instead of "successful / unsuccessful" | Resolved | 2019-10-25 | 2019-10-25 | LF & YL

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | UI | Visibility is poor for login page (black text on dark purple background) | Low | 1 | 27 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | ProcessLogin | Failed to redirect to the targeted page | High | 5
3 | 1 | Bootstrap | Checked the wrong columns for pre-requisite.csv | High | 5
4 | 1 | Bootstrap | Bootstrap errors output not sorted accordingly to the JSON requirements | Low | 1
5 | 1 | Login (admin) | No logout button in bootstrap.php that admin is directed to | High | 5
6 | 1 | Bootstrap | Bootstrap does not work on AWS after deployment | Critical | 10
7 | 2 | Bootstrap Validation | Bootstrap proceeds to check file-specific validations after detecting a blank field | High | 5 | 87 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
8 | 2 | Bootstrap Validation | Bootstrap does not check for exam start & end time properly | High | 5
9 | 2 | Rounds Clearing | Clicking on "Start Round" in Round 1 does not direct the admin to bootstrap | Critical | 10
10 | 2 | Rounds Clearing | Clicking on "Import" at bootstrap without uploading bootstrap file starts the round | High | 5
11 | 2 | Edit Bid | Missing token authentication, fails to proceed, redirected to login | High | 5
12 | 2 | Bid | Total bidded amount calculation works incorrectly, resulting in wrong E-dollar amount in database | High | 5
13 | 2 | JSON Bootstrap | Failed to check for special condition in bootstrap | High | 5
14 | 2 | Edit Bid | Missing some necessary validations | High | 5
15 | 2 | Rounds Clearing | Rounds display "Successful / Unsuccessful" instead of "Success / Fail" | Low | 1
16 | 2 | Rounds Clearing | Bid results only display for admin after clicking "clear round", refreshing the page will remove the bid results | High | 5
17 | 2 | Rounds Clearing | A bid that should be successful went through as unsuccessful | High | 5
18 | 2 | Rounds Clearing | Admin main page does not display "round is currently ongoing / inactive" after round 2 starts | Low | 1
19 | 2 | Edit Bid | Bid can still be dropped after round closes, user will get back double the credits if bid failed, and will get back the credits if bid succeeded | High | 5
20 | 2 | Edit Bid | If a user types in valid course code, section, amount but it does not exist in "bidded", the user will be bounced back to the main page (nothing changes) | High | 5
21 | 2 | AWS Deployment - section dump JSON | Section Dump does not work on AWS | High | 5
22 | 2 | AWS Deployment - JSON checker | Test Case 115-bootstrap.txt does not work on AWS | High | 5
23 | 2 | Add Bid | Bid is created as object in one function but as list in another, causing some functions to not work | Critical | 10
24 | 3 | JSON | Section Dump, Bid Dump, delete Bid, Drop Section, Update Bid Files need to be upper case. | High | 5 | 41 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
25 | 3 | Edit Bid | Edit bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | High | 5
26 | 3 | Add Bid | Add bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | High | 5
27 | 3 | Add Bid | Round 2 for Add bid, System did not validate if the user did enter amount higher than the Minimum Bid Required | High | 5
28 | 3 | View Bidding Results | Min Bid Required reflects "14" although the user bidded for 12 and succeeded | High | 5
29 | 3 | Rounds Clearing | Ben's bid is stored as "Success" although it is lower than the minimum amount | High | 5
30 | 3 | Add Bid | Error displayed when trying to add a bid | Critical | 10
31 | 3 | Round 2 | Bid Result displays "Pending" instead of "successful / unsuccessful" | Low | 1
32 | 3
33 | 3
29 | 4 |  |  |  |  | 0 | Use the planned debugging time in the iteration.
30 | 4
31 | 4
32 | 4
33 | 5 |  |  |  |  | 0 | Use the planned debugging time in the iteration.
34 | 5
35 | 5
36 | 5
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198