## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | UI | Visibility is poor for login page (black text on dark purple background) | Resolved | 2019-09-27 | 2019-09-30 | C & WT
2 | 1 | ProcessLogin | Failed to redirect to the targeted page | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
3 | 1 | Bootstrap | Checked the wrong columns for pre-requisite.csv | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
4 | 1 | Bootstrap | Bootstrap errors output not sorted accordingly to the JSON requirements | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
5 | 1 | Login (admin) | No logout button in bootstrap.php that admin is directed to | Resolved | 2019-09-30 | 2019-09-30 | TY & YL
6 | 1 | Bootstrap | Bootstrap does not work on AWS after deployment | Resolved | 31/09/2019 | 2019-10-12 | By IS212 team
7 | 2 | Bootstrap Validation | Bootstrap proceeds to check file-specific validations after detecting a blank field | Resolved | 2019-10-05 | 2019-10-05 | TY & LF
8 | 2 | Bootstrap Validation | Bootstrap does not check for exam start & end time properly | Resolved | 2019-10-05 | 2019-10-05 | TY & LF
9 | 2 | Rounds Clearing | Clicking on "Start Round" in Round 1 does not direct the admin to bootstrap | Resolved | 2019-10-10 | 2019-10-10 | TY & LF
10 | 2 | Rounds Clearing | Clicking on "Import" at bootstrap without uploading bootstrap file starts the round | Resolved | 2019-10-10 | 2019-10-18 | Remark: Is not a bug
11 | 2 | Edit Bid | Missing token authentication, fails to proceed, redirected to login | Resolved | 2019-10-10 | 2019-10-11 | C & YL
12 | 2 | Bid | Total bidded amount calculation works incorrectly, resulting in wrong E-dollar amount in database | Resolved | 2019-10-11 | 2019-10-12 | C & YL
13 | 2 | JSON Bootstrap | Failed to check for special condition in bootstrap | Resolved | 2019-10-11 | 2019-10-11 | WT & C
14 | 2 | Edit Bid | Missing some necessary validations | Resolved | 2019-10-11 | 2019-10-12 | C & YL
15 | 2 | Rounds Clearing | Rounds display "Successful / Unsuccessful" instead of "Success / Fail" | Resolved | 2019-10-11 | 2019-10-12 | TY & LF
16 | 2 | Rounds Clearing | Bid results only display for admin after clicking "clear round", refreshing the page will remove the bid results | Resolved | 2019-10-12 | 2019-10-13 | TY & LF
17 | 2 | Rounds Clearing | A bid that should be successful went through as unsuccessful | Resolved | 2019-10-12 | 2019-10-13 | TY & LF
18 | 2 | Rounds Clearing | Admin main page does not display "round is currently ongoing / inactive" after round 2 starts | Resolved | 2019-10-13 | 2019-10-13 | TY & LF
19 | 2 | Edit Bid | Bid can still be dropped after round closes, user will get back double the credits if bid failed, and will get back the credits if bid succeeded | Resolved | 2019-10-13 | 2019-10-13 | C & YL
20 | 2 | Edit Bid | If a user types in valid course code, section, amount but it does not exist in "bidded", the user will be bounced back to the main page (nothing changes) | Resolved | 2019-10-13 | 2019-10-13 | C & YL
21 | 2 | AWS Deployment - section dump JSON | Section Dump does not work on AWS | Resolved | 2019-10-13 | 2019-10-13 | TY & LF
22 | 2 | AWS Deployment - JSON checker | Test Case 115-bootstrap.txt does not work on AWS | Resolved | 2019-10-13 | 2019-10-14 | TY & LF
23 | 2 | Add Bid | Bid is created as object in one function but as list in another, causing some functions to not work | Resolved | 2019-10-13 | 2019-10-14 | TY & LF
24 | 3 | JSON | Section Dump, Bid Dump, delete Bid, Drop Section, Update Bid Files need to be upper case. | Resolved | 2019-10-22 | 2019-11-22 | TY & WT
25 | 3 | Edit Bid | Edit bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | Resolved | 2019-10-22 | 2019-10-27 | TY & LF
26 | 3 | Add Bid | Add bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | Resolved | 2019-10-22 | 2019-10-22 | C & YL
27 | 3 | Add Bid | Round 2 for Add bid, System did not validate if the user did enter amount higher than the Minimum Bid Required | Resolved | 2019-10-22 | 2019-10-22 | C & YL
28 | 3 | View Bidding Results | Min Bid Required reflects "14" although the user bidded for 12 and succeeded | Resolved | 2019-10-23 | 2019-10-24 | TY & WT
29 | 3 | Rounds Clearing | Ben's bid is stored as "Success" although it is lower than the minimum amount | Resolved | 2019-10-24 | 2019-10-25 | LF & YL
30 | 3 | Add Bid | Error displayed when trying to add a bid | Resolved | 2019-10-25 | 2019-10-25 | LF & YL
31 | 3 | Round 2 | Bid Result displays "Pending" instead of "successful / unsuccessful" | Resolved | 2019-10-25 | 2019-10-25 | LF & YL
32 | 3 | Edit Bid | Edit bid does not load information for side navbar if round status is not started | Resolved | 26/10/2019 | 26/10/2019 | C & YL
33 | 3 | Add Bid | Add bid does not check for vacancy; people can bid for sections that are full | Resolved | 2019-10-27 | 2019-10-28 | LF & YL
34 | 3 | Add Bid | Add bid in round 2, size does not account for round 1 successful bids | Resolved | 2019-10-27 | 2019-10-28 | TY & WT
35 | 3 | Add Bid | Duplicate error messages when trying to add bid when round not started | Resolved | 2019-10-28 | 2019-10-28 | TY & WT
36 | 3 | Add Bid | User can bid when it's round 1 not started | Resolved | 2019-10-28 | 2019-10-29 | C & YL
37 | 3 | Add Bid | User is shown logic validation when entering a wrong input when adding bid (should only display input validation) | Resolved | 2019-10-28 | 2019-10-29 | C & YL
38 | 3 | Edit Bid (admin) | Edited bid by admin is only reflected after refreshing | Resolved | 2019-10-29 | 2019-10-30 | LF & YL
39 | 3 | User UI | Completed courses page has no UI for header | Resolved | 2019-10-29 | 2019-10-30 | C & WT
40 | 3 | Admin UI | UI does not grid properly | Resolved | 2019-10-29 | 2019-10-29 | LF & WT
41 | 3 | Admin UI | Admin UI fades slightly after clicking "show all data" in AWS | Resolved | 2019-10-29 | 2019-10-30 | LF & YL
42 | 4 | Database / Bootstrap | constraint for SectionID set too tightly in database, failing bootstrap | Resolved | 2019-10-29 | 2019-10-30 | LF & YL
43 | 4 | Add Bid | Unable to bid with 2 decimal places | Resolved | 2019-10-29 | 2019-10-30 | LF & YL
44 | 4 | Add Bid | When exam timetable clashes, error message says lesson timetable clashes instead | Resolved | 2019-10-29 | 2019-10-30 | LF & YL
45 | 4 | Add Bid for Round 2 | User are not able to see the courses in Round 2 due to some errors in the code | Resolved | 2019-11-05 | 2019-11-05 | LF & YL

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | UI | Visibility is poor for login page (black text on dark purple background) | Low | 1 | 27 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | ProcessLogin | Failed to redirect to the targeted page | High | 5
3 | 1 | Bootstrap | Checked the wrong columns for pre-requisite.csv | High | 5
4 | 1 | Bootstrap | Bootstrap errors output not sorted accordingly to the JSON requirements | Low | 1
5 | 1 | Login (admin) | No logout button in bootstrap.php that admin is directed to | High | 5
6 | 1 | Bootstrap | Bootstrap does not work on AWS after deployment | Critical | 10
7 | 2 | Bootstrap Validation | Bootstrap proceeds to check file-specific validations after detecting a blank field | High | 5 | 87 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
8 | 2 | Bootstrap Validation | Bootstrap does not check for exam start & end time properly | High | 5
9 | 2 | Rounds Clearing | Clicking on "Start Round" in Round 1 does not direct the admin to bootstrap | Critical | 10
10 | 2 | Rounds Clearing | Clicking on "Import" at bootstrap without uploading bootstrap file starts the round | High | 5
11 | 2 | Edit Bid | Missing token authentication, fails to proceed, redirected to login | High | 5
12 | 2 | Bid | Total bidded amount calculation works incorrectly, resulting in wrong E-dollar amount in database | High | 5
13 | 2 | JSON Bootstrap | Failed to check for special condition in bootstrap | High | 5
14 | 2 | Edit Bid | Missing some necessary validations | High | 5
15 | 2 | Rounds Clearing | Rounds display "Successful / Unsuccessful" instead of "Success / Fail" | Low | 1
16 | 2 | Rounds Clearing | Bid results only display for admin after clicking "clear round", refreshing the page will remove the bid results | High | 5
17 | 2 | Rounds Clearing | A bid that should be successful went through as unsuccessful | High | 5
18 | 2 | Rounds Clearing | Admin main page does not display "round is currently ongoing / inactive" after round 2 starts | Low | 1
19 | 2 | Edit Bid | Bid can still be dropped after round closes, user will get back double the credits if bid failed, and will get back the credits if bid succeeded | High | 5
20 | 2 | Edit Bid | If a user types in valid course code, section, amount but it does not exist in "bidded", the user will be bounced back to the main page (nothing changes) | High | 5
21 | 2 | AWS Deployment - section dump JSON | Section Dump does not work on AWS | High | 5
22 | 2 | AWS Deployment - JSON checker | Test Case 115-bootstrap.txt does not work on AWS | High | 5
23 | 2 | Add Bid | Bid is created as object in one function but as list in another, causing some functions to not work | Critical | 10
24 | 3 | JSON | Section Dump, Bid Dump, delete Bid, Drop Section, Update Bid Files need to be upper case. | High | 5 | 67 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
25 | 3 | Edit Bid | Edit bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | High | 5
26 | 3 | Add Bid | Add bid did not check for 2 decimal place and display error message when user enter amount more than 2 decimal place | High | 5
27 | 3 | Add Bid | Round 2 for Add bid, System did not validate if the user did enter amount higher than the Minimum Bid Required | High | 5
28 | 3 | View Bidding Results | Min Bid Required reflects "14" although the user bidded for 12 and succeeded | High | 5
29 | 3 | Rounds Clearing | Ben's bid is stored as "Success" although it is lower than the minimum amount | High | 5
30 | 3 | Add Bid | Error displayed when trying to add a bid | Critical | 10
31 | 3 | Round 2 | Bid Result displays "Pending" instead of "successful / unsuccessful" | Low | 1
32 | 3 | Edit Bid | Edit bid does not load information for side navbar if round status is not started | Low | 1
33 | 3 | Add Bid | Add bid does not check for vacancy; people can bid for sections that are full | High | 5
34 | 3 | Add Bid | Add bid in round 2, size does not account for round 1 successful bids | High | 5
35 | 3 | Add Bid | Duplicate error messages when trying to add bid when round not started | Low | 1
36 | 3 | Add Bid | User can bid when it's round 1 not started | High | 5
37 | 3 | Add Bid | User is shown logic validation when entering a wrong input when adding bid (should only display input validation) | High | 5
38 | 3 | Edit Bid (admin) | Edited bid by admin is only reflected after refreshing | Low | 1
39 | 3 | User UI | Completed courses page has no UI for header | Low | 1
40 | 3 | Admin UI | UI does not grid properly | Low | 1
41 | 3 | Admin UI | Admin UI fades slightly after clicking "show all data" in AWS | Low | 1
42 | 4 | Database / Bootstrap | constraint for SectionID set too tightly in database, failing bootstrap | Critical | 10 | 26 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
43 | 4 | Add Bid | Unable to bid with 2 decimal places | Critical | 10
44 | 4 | Add Bid | When exam timetable clashes, error message says lesson timetable clashes instead | Low | 1
45 | 4 | Add Bid for Round 2 | User are not able to see the courses in Round 2 due to some errors in the code | High | 5
46 | 4
47 | 4
48 | 4
49 | 5 |  |  |  |  | 0 | Use the planned debugging time in the iteration.
50 | 5
51 | 5
52 | 5
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123