## Slide 1: G8T9 Y W L T C
PM Review
Christine | Lifu | Tee Yong | Wang Ting | Yu Liang

## Slide 2: Functionalities

## Slide 3: Do you plan to drop/add any functionalities?
Not dropping any functionalities
Yes, we plan to add functionalities
Starting with recommended ones after completing required functions
Timetable
Search
Consideration for other functions will depend on progress

## Slide 4: Do you plan to use any PHP frameworks?
Didn’t use in Iter 1
Plan to utilize PHP frameworks in future iterations (need to learn)

## Slide 5: Did you manage to finish login + 1 functionality?
Login : Yes

## Slide 6: Did you manage to finish login + 1 functionality?
1 Functionality - Bootstrap
Largely complete
(with validation)
(yet to implement bidding rounds)

## Slide 7: What is the IP address & admin password for your cloud deployment?
Admin password = P@ssw0rd!547
Cloud IP Address = 13.58.117.140

## Slide 8: Schedule

## Slide 9: Project Overall Schedule
Iteration 1 – Login + Bootstrap + Basic UI design
Iteration 2 – Finish all required functionalities
Iteration 3 – Develop additional features + finish UI
Iteration 4 – Fix any bugs, UI, app finalization & deployment
Iteration 5 – Final Presentation

## Slide 10: Project Schedule
Week 5 – Week 6
W5
Week 7 – Week 8
W7
W8
Week 9 – Week 10
W9
W10
Week 11 – Week 13
W11
W12
W13
Iteration 2
(Rounds + user functionalities)
Iteration 3
(Prepare for user testing)
Iteration 4
(Develop additional features)
Iteration 5
(Finishing touch + presentation)
Iteration 1
(Login + Bootstrap)
W6
Not started
Completed
Not started
Not started
Not started
LEGEND
PLANNED
ACTUAL

## Slide 11: Iteration 1 (17/9 – 1/10)
Iteration 1
UI ideation & implementation
Login + database connection
Main page + Logout
Bootstrap & Testing
PLANNED TASKS
SQL + Objects & DAOs
Completed
20/9
21/9
22/9
23/9
24/9
25/9
26/9
27/9
28/9
29/9
30/9
31/9 – 1/10
LEGEND
SCHEDULED
ACTUAL
Completed
Completed
HOLD
Completed
Completed
Completed
HOLD
Completed
Deployment + PM Review
Completed

## Slide 12: Iteration 2 (2/10 – 15/10)
Iteration 2
Rounds
Add / Drop Bid / Section
Additional Feature
Testing & Deployment
PLANNED TASKS
JSON Validations
2/10 – 3/10
3/10
4/10
5/10
6/10
7/10
8/10
9/10
10/10
11/10
12/10
13/10 - 15/10
LEGEND
PLANNED
ACTUAL
Others

## Slide 13: Iteration 3 (16/10 – 29/10)
Iteration 3
Organizing, tidying up
Testing
Presentation Preparation
Deployment
PLANNED TASKS
Incomplete / Additional features
16/10
17/10
18/10
19/10
20/10
21/10
22/10
23/10
24/10
25/10
26/10
27/10 - 29/10
LEGEND
PLANNED
ACTUAL
Others

## Slide 14: Iteration 4 (30/10 – 9/11)
Iteration 4
Organizing, tidying up
Testing
Deployment
Preparation
PLANNED TASKS
Fixing features & UI
30/10
31/10
1/11
2/11
3/11
4/11
5/11
6/11
7/11
8/11
9/11
LEGEND
PLANNED
ACTUAL

## Slide 15: Iteration 5 (9/11 – 19/11)
Iteration 5
Deployment & Submission
Presentation
PLANNED TASKS
Presentation Preparation
10/11
11/11
12/11
13/11
14/11
15/11
16/11
17/11
18/11
19/11
LEGEND
PLANNED
ACTUAL

## Slide 16: What are your milestones?
Milestone 1 – PM Review
Milestone 2 – In-class Demo
Milestone 3 – User Acceptance Test
Milestone 4 – Deployment
Milestone 5 – Final Presentation

## Slide 17: Iteration 1 Critical Path
1
3
1
3
3
3.1.1
0
4
4
5
5
1
3.2.2
1
6
6
6
6
1
3.3.1
0
7
9
7
9
3
3.4.2
0
7
9
10
12
3
3.4.1.2
3
10
10
10
10
1
3.5.1.1
0
13
14
13
14
2
5
0
4
5
4
5
2
3.2.1
0
11
12
11
12
2
3.5.1.2
0
Task ID | Description | Effort
3.1.1 | Create SQL | 3
3.2.1 | Create objects & DAOs | 2
3.2.2 | Set up connection to database | 1
3.3.1 | Create Login | 1
3.4.2 | Create Main page & Logout | 3
3.4.1.2 | Create Login Page UI | 3
3.5.1.1 | Create Bootstrap without validation | 1
3.5.1.2 | Create Bootstrap with validation | 2
5 | Deployment | 2

## Slide 18: How much buffer time do you have?
4 days

## Slide 19: Bug Metrics

## Slide 20
Bug Metrics
S/N | Description | Severity | Status
1 | UI - Poor visibility for login page (black text on dark purple BG) | 1 – Low | Resolved
2 | ProcessLogin - Process login failed to redirect to targeted page | 5 – High | Resolved
3 | Bootstrap - Checked wrong columns for pre-requisite.csv | 5 – High | Resolved
4 | Bootstrap – errors output not sorted accordingly to requirements | 1 – Low | Resolved
5 | Login (admin) - No logout button in bootstrap.php after admin login | 5 – High | Resolved

## Slide 21: Roles & Responsibilities

## Slide 22: Iteration 1 – Roles & Responsibilities
Project Manager – Huang Lifu
Coding Team 1 – Yu Liang & Tee Yong
Coding Team 2 – Wang Ting & Christine

## Slide 23: Pair Programming Teams & Rotation Plan

## Slide 24: Pair Programming Teams & Rotation Plan
Iteration | Project Manager | Programming Pairs
1 | Lifu | Yu Liang & Tee Yong Wang Ting & Christine
2 | Wang Ting | Lifu & Tee Yong Yu Liang & Christine
3 | Christine | Yu Liang & Lifu Tee Yong & Wang Ting
4 | Tee Yong | Lifu & Christine Yu Liang & Wang Ting
5 | Yu Liang | N/A

## Slide 25: Thank you!